## Slide 1: ARTICLE 5. Middle School Building Project

## Slide 2
Ms. Guarriello moves that the meeting take affirmative action on Article 5 as printed in the warrant to appropriate the amount of $7,200,000 for the purposes stated in Article 5 and authorize the Treasurer with the approval of the Select Board to raise such amount by borrowing, subject to an affirmative debt exclusion vote of the Town, all as set forth in Article 5.
ARTICLE 5: Middle School Building Project

## Slide 3: A Year in Review: Costs
STM Approved
$102,816,000
ARTICLE 5: Middle School Building Project
2022 |  |  |  |  |  |  |  |  |  |  |  | 2023
Jan | Feb | Mar | Apr | May | Ju | Jul | Aug | Sep | Oct | Nov | Dec | Jan
60% CD Estimate
$108,783,060
(DD) Estimate
$108,415,174
90% CD Estimate
$109,795,813
Detailed Design (DD)
Phase
Construction Document (CD)
Phase
Ballot Passed
VE -$1,879,261
VE -$110,931

## Slide 4: Breakdown of Additional Funding Request
ARTICLE 5: Middle School Building Project
Project Cost | Cost @ STM ‘22 | Current Cost | Variance
Const. Cost | $80,772,477 | $87,420,207 | $6,647,730
Soft Cost | $12,599,080 | $12,599,080 | 0
FF&E / Tech | $2,625,000 | $2,625,000 | 0
Contingency | $4,799,828 | $5,132,214 | $332,386
Sub-Total | $100,796,385 | $107,776,501 | $6,980,116
Bid Contingency *Only if needed | $2,019,312 | $2,019,312 | 0
Total | $102,815,697 | $109,795,813 | $6,980,116

## Slide 5: What has changed in the last year?
Building Design? NO
Economy? YES
  Inflation * Supply Chain * Workforce Challenges
ARTICLE 5: Middle School Building Project

## Slide 6: Budget Deficits in Other Public School Projects
ARTICLE 5: Middle School Building Project
District | Type | Budget | Bid /Estim. | % Over | Pass
Andover | Elem | $119.2M | $136.3M | +14.3% | Yes
Groton | Elem | $61.0M | $70.5 | +15.6% | Yes
Westwood | Elem | $70.0M | $74.0M | +5.7% | Yes
Swampscott | Elem | $76.5M | $79.7M | +4.1% | Yes
Somerset | Middle | $69.0M | $79.0M | +14.5% | No
Nauset | High | $104.7M | $134.4 | +28.4% | Yes
Stoneham | High | $189.6M | $214.6M | +13.1% | Yes

## Slide 7
Concord Middle School Building Committee Priorities:
  Educational Plan Implementation
  Net-zero Ready Design
  Enlarged Gym+ Auditorium as shared educational and community spaces
  Durability and Maintenance
ARTICLE 5: Middle School Building Project

## Slide 8
ARTICLE 5: Middle School Building Project
Concord Middle School Building Committee Value Engineering/Value Management :
  $6,184,098 in construction cost savings
  +80 items considered over 24 hours of deliberations and CMSBC meetings

## Slide 9: Impact of “YES” Vote
Project goes out to Bid (March 2023)
Construction Begins (April 2023)
School Opens (Feb 2025)
Demo Sanborn + Field Completion (Sept 2026)
ARTICLE 5: Middle School Building Project

## Slide 10
ARTICLE 5: Middle School Building Project
Impact of “NO” Vote
1. Educational impact to current and future CMS Students
2. Increase cost to the Town
  a. Re-Design to $102.8
    Delays will Occur (6-9mo minimum)
    Major Scope Reductions (estimated at $12.4M in scope)
        Uncertain but assume: Reduced Program Spaces, Smaller Gym, Smaller (or no) Auditorium, and Reduced Fields and Landscape
  b. Put “in Drawer” for future project
    Annual Escalation assumed at 7% or $7M/annually on $100m
3. Unknown Maintenance and Emergency costs at Sanborn + Peabody

## Slide 11: Preliminary Tax Impact Analysis:
Additional Funding Request $7.2 million
Estimated Cost/Year Per $100,000 valuation $6.28 per $100,000
Estimated Average Cost/Year increase
for the median home valued at $1,169,500 $73.44
ARTICLE 5: Middle School Building Project

## Slide 12
Ms. Guarriello moves that the meeting take affirmative action on Article 5 as printed in the warrant to appropriate the amount of $7,200,000 for the purposes stated in Article 5 and authorize the Treasurer with the approval of the Select Board to raise such amount by borrowing, subject to an affirmative debt exclusion vote of the Town, all as set forth in Article 5.
ARTICLE 5: Middle School Building Project